# QWeave Three Week Team Execution Plan

Four-person work division, integration rhythm, and submission gates

Team: Shrivardhini N | Atharva Sheersh Pandey | Diptesh Das | Haridasu Sreedhar

Guide: Prof. Bhuvaneswari M  |  Planning horizon: 21 days  |  Version: 1.0

# Operating Principle

The team should work in parallel but integrate daily. Each workstream has one directly responsible owner and one reviewer. Proofs are not a separate writing exercise at the end: every formal invariant must be paired with an implementation assertion and test during development. The allocations below are a balanced starting point and may be swapped if skills differ.

Figure 1. Twenty-one-day critical path. Workstreams overlap, but result and manuscript freezes are fixed.

# 1 Role Allocation

| Person | Primary ownership | Secondary ownership | Final accountable outputs |
| --- | --- | --- | --- |
| Atharva Sheersh Pandey | Integration lead; Qiskit IR, target adapter, experiment harness | Repository, CI, final artifact build | End-to-end compiler command; immutable experiment records; release tag |
| Shrivardhini N | Mathematical lead; formal model, proofs, equivalence strategy | Paper methods and limitations | LaTeX theorem section; proof-to-test matrix; correctness review |
| Diptesh Das | Deterministic optimisation lead; initial mapping, fallback router, baselines | Small-instance CP-SAT oracle | Mapper and fallback modules; SABRE/oracle comparisons; ablation outputs |
| Haridasu Sreedhar | Learning lead; Gymnasium environment, GNN, masked PPO | Training diagnostics and topology generalisation | Policy code and checkpoints; training logs; learning ablations |

Guide checkpoint. Prof. Bhuvaneswari M should review the frozen research question on Day 2, the proof boundary and preliminary pipeline on Day 8, the result interpretation on Day 17, and the final manuscript on Day 20.

# 2 Review Pairing and Bus-Factor Control

| Workstream | Owner | Reviewer | Required handoff artifact |
| --- | --- | --- | --- |
| Compiler integration | Atharva | Diptesh | Interface tests and sample routed circuit |
| Formal proofs | Shrivardhini | Atharva | Assumption list, theorem source, linked assertions |
| Mapper/fallback/baselines | Diptesh | Shrivardhini | Objective trace, termination tests, baseline parity |
| GNN-PPO | Haridasu | Atharva | Environment checker, masked-policy tests, training dashboard |
| Scheduler | Shrivardhini | Diptesh | Feasibility tests, lower-bound calculations, makespan report |
| Statistics and figures | Atharva | Haridasu | Frozen analysis script and regenerated figures |
| Manuscript | Shrivardhini | All authors | Compiled PDF, response checklist, contribution statement |

# 3 Daily Plan

| Day | Focus | Parallel assignments | Exit evidence |
| --- | --- | --- | --- |
| 1 | Kick-off and scope freeze | Atharva: repo/env spike. Shrivardhini: formal objects. Diptesh: baselines and mapper spec. Haridasu: RL state/action draft. | One-page research contract; repository skeleton; initial bibliography. |
| 2 | Interfaces and datasets | Agree dataclasses and target adapter. Select circuits/topologies and create train/validation/test manifest. | Interface document; immutable split manifest; guide review. |
| 3 | Baseline gate | Run Qiskit SABRE and basic routing on smoke circuits. Establish metrics and validation skeleton. | Baseline CSV/JSON; reproducible seed; Gate A passed. |
| 4 | Core implementations | Mapper and scheduler coding; Gymnasium environment scaffold; theorem assumptions and invariants. | Unit tests for graphs, mapping, ready set, resources. |
| 5 | Deterministic routing | Implement fallback shortest-path router and final-layout bookkeeping; policy feature builder. | Legal routed outputs on paths/grids; mapping trace. |
| 6 | End-to-end deterministic path | Integrate mapper, fallback, scheduler, validation; implement GNN actor-critic forward pass. | One command compiles smoke suite; PyG tensors validated. |
| 7 | Core gate | Stress deterministic pipeline and exact oracle on tiny cases; fix interfaces before learning integration. | Gate B passed; no open interface redesign. |
| 8 | Masked policy integration | Connect GNN scores to edge actions and EXECUTE; prove/verify zero probability for illegal actions. | Environment checker passes; action-mask property tests. |
| 9 | PPO rollout | Implement trajectory buffer, GAE, clipped loss, entropy and value losses; start tiny curriculum. | Short training run improves shaped return without invalid actions. |
| 10 | Scheduler feedback | Feed realised or incremental depth signals into routing reward; monitor fallback and cycles. | Reward decomposition logs; scheduler lower-bound report. |
| 11 | Learning gate | Run end-to-end learned routing on validation circuits; profile bottlenecks and memory. | Gate C learning milestone; selected architecture fixed. |
| 12 | Curriculum and tuning | Limited hyperparameter search on validation set only; expand circuit width/topology diversity. | Candidate configs and deterministic comparison notebook/script. |
| 13 | Robustness | Topology holdout evaluation, failure analysis, watchdog tuning, proof assumption audit. | Generalisation table draft; failure taxonomy. |
| 14 | Training freeze | Choose one primary model and one backup. Freeze reward weights, architecture, seeds, and timeouts. | Signed configuration hash; test set still unopened. |
| 15 | Main experiments | Run all baselines and QWeave on test circuits. Validate every output and preserve failures. | Per-circuit raw result bundle, run manifests, logs. |
| 16 | Ablations and statistics | Run required ablations; calculate paired deltas, bootstrap intervals, tests, and effects. | Tables and main plots regenerated from scripts. |
| 17 | Results freeze | No method changes. Review anomalies, timeouts, and negative results; write exact claims. | Gate D passed; result table frozen and checksummed. |
| 18 | Paper assembly | Integrate methods, proofs, experiments, results, threats, data statement, and related work. | Complete first full manuscript; all figures final-size readable. |
| 19 | Manuscript freeze | Internal review for claim/evidence alignment, citations, theorem assumptions, and reproducibility. | Gate E draft; no new experiments unless correcting an error. |
| 20 | Guide and venue review | Apply guide feedback; format target template; anonymise if required; verify quartile/scope and costs. | Submission-ready manuscript, supplement, cover letter draft. |
| 21 | Release and submission bundle | Fresh-clone reproduction test; tag repository; archive release; final author approvals. | Release artifact, final PDFs/source, checklist, submission package. |

# 4 Person-Level Deliverables

## Atharva Sheersh Pandey

Qiskit pass integration and CLI

Target/circuit adapters and shared dataclasses

Experiment runner, configuration hashing, CI, release

Statistical aggregation and regenerable figures

Final repository and artifact reproducibility test

## Shrivardhini N

Formal problem model and assumption register

Mapping, legality, equivalence, scheduler, and termination proofs

Depth-aware scheduler and feasibility checker

Proof-linked property/equivalence tests

Methods, theory, limitations, and final manuscript integration

## Diptesh Das

Weighted interaction graph and initial mapping

Strict-improvement local search and trace

Deterministic shortest-path fallback

SABRE/basic baselines and small CP-SAT oracle

Mapper/fallback/oracle ablations and runtime analysis

## Haridasu Sreedhar

Gymnasium environment and graph observations

PyG message-passing actor-critic

Masked edge-action distribution and PPO trainer

Curriculum, checkpoints, diagnostics, and topology holdout

No-GNN/no-shaping/no-learning ablations

# 5 Daily Integration Rhythm

09:00-09:15: stand-up. State yesterday's evidence, today's measurable exit, and blockers.

13:00: interface checkpoint. Merge contract changes before dependent work continues.

18:00: integration window. Owner demonstrates tests/results; reviewer approves or returns specific issues.

18:30: automated smoke run and artifact upload. Main must remain green overnight.

Twice weekly: 30-minute claim audit. Each manuscript sentence labelled proof, measured result, interpretation, or future work.

## 5.1 Pull Request Rules

One logical change per pull request; no direct commits to main after Day 3.

Every algorithm change includes or updates tests and a short complexity/assumption note.

Every experiment change updates a versioned config; never overwrite raw results.

Proof-affecting code requires mathematical-lead review. Metric-affecting code requires integration-lead review.

A reviewer reproduces one representative command before approval.

# 6 RACI for Critical Decisions

| Decision | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Research question and scope | All | Guide + Atharva | All | All |
| Formal assumptions and theorem wording | Shrivardhini | Shrivardhini | Atharva, Diptesh | Haridasu |
| Compiler interfaces | Atharva | Atharva | Diptesh, Haridasu | Shrivardhini |
| Reward and model architecture | Haridasu | Haridasu | Shrivardhini, Atharva | Diptesh |
| Baseline and oracle settings | Diptesh | Diptesh | Atharva, Shrivardhini | Haridasu |
| Results freeze and paper claims | All | Guide + Shrivardhini | All | All |
| Venue and submission | Atharva, Shrivardhini | Guide | All | All |

# 7 Risk and Contingency Plan

| Risk trigger | Immediate response | Protected paper contribution |
| --- | --- | --- |
| PPO fails to beat heuristic by Day 13 | Stop broad tuning; use learned reranking on a small candidate set or present negative ablation honestly | Proof-backed safe compiler and rigorous evaluation remain |
| Training too slow | Reduce width/curriculum; parallelise environments; freeze deterministic core | Correctness, mapper, scheduler, oracle comparisons |
| Equivalence failures | Block experiments; isolate final-layout or direction/decomposition bug | No invalid result enters the paper |
| Exact solver times out | Restrict oracle to tiny instances and report optimality bounds/timeouts | Oracle remains a sanity reference |
| Insufficient novelty for Q1/Q2 | Strengthen proof-to-implementation linkage and topology-holdout evidence; do not inflate claims | Submission may move to a better-fit venue after advisor review |
| One member unavailable | Reviewer assumes owner role using mandatory handoff artifacts | Daily integration prevents single-person knowledge silos |

# 8 Freeze Checklists

## 8.1 Day 14 Training Freeze

Primary and backup checkpoints selected

Config, environment, split, and source commit hashes recorded

No test data inspected

Reward components and metric code unit-tested

Fallback threshold fixed

## 8.2 Day 17 Results Freeze

All outputs validated

All failures/timeouts included

Ablations complete

Paired statistics regenerated

Claims written with exact numbers and uncertainty

Raw results immutable

## 8.3 Day 21 Submission Freeze

Fresh-clone reproduction passes

Paper source compiles without warnings affecting output

Author names, affiliations, emails, order, and contributions approved

Venue scope/quartile/cost rechecked

Ethics, data, code, conflict, and AI-use statements complete

Repository release archived and cited

# 9 Final Team Rule

If a feature does not strengthen the main claim, a proof obligation, a required baseline, or reproducibility, it is out of scope until after submission. Depth minimisation is the headline; safety, correctness, and transparent evidence are what make the headline publishable.